## A. Template Instructions
CalRHT EHR Modernization Grant Program Workplan Template Instructions
GENERAL INSTRUCTIONS | Complete workplan tab B. EHR Workplan Template. A sample workplan is provided in tab C for reference; no edits needed in tab C.
REQUIRED GOALS | The workplan must include activities to support the following goals: 1) Illustrate a thorough approach to EHR selection and implementation that incorporates interoperability and timely go live by September 30, 2027. 2) Demonstrate compliance with all program requirements per the Grant Guide, including DxF connectivity, reporting, cybersecurity attestation, and sustainability. 3) Applicant approach aligns with rural collaborative and regional collaborative goals and strategy.
REQUIRED WORKPLAN ELEMENTS | 1. Vendor Selection and Implementation Plan — Approach to selecting an EHR vendor/implementation partner, evaluation criteria, procurement process, and expected contract execution date. Named vendor, LOI, or vendor attestation scores more competitively. Applicants should reference completion of Technology Readiness Assessment with the workplan.
2. California Data Exchange Framework (DxF) Connectivity Plan — Describe: (a) current DSA signatory status, (b) current QHIO connection or national network participation status, and (c) planned approach to greater data exchange and connectivity. DxF connectivity is a Milestone 3 requirement.
3. Reporting Plan — Aligned to required reporting cadences: streamlined monthly subrecipient activity and financial reporting; streamlined quarterly financial and performance reports; annual Activity Reports; and annual Financial Reports.
4. Cybersecurity and Privacy Plan — Applicants will attest that EHR implementation will comply with applicable federal cybersecurity requirements, and that the organization has (or will have by grant execution) a cybersecurity plan consistent with HHS Health Industry Cybersecurity Practices (HICP). A standardized security risk assessment is required for Milestone 3.
OTHER WORKPLAN DETAILS | a) A time frame to reflect the funding cycle
b) Identified roles responsible for the workplan element
c) Estimated dates to initiate and end activities. We recognize that EHR implementations are variable in timing but anticipate an approximate estimate based on your plans for the replacement implementation. Timeline can assume a tentative Sept/Oct 2026 award timeline as means of where vendor engagement, etc., may be impacted; Grant completion must be by 9/30/2027.
d) Associated outcomes or measures
e) Interval reflects activities that are repeated at regular intervals (monthly, quarterly, annually), e.g. reporting based on program requirements. Select only if the activity is repeated and indicate the time frame for start and end dates only for the first interval.

## B. EHR Workplan Template
CalRHT EHR Modernization Grant — Workplan Template
Workplan Element | Activity | Person Responsible | Key Partners (if applicable) | Start Date | End Date | Interval (if applicable) | Outcome(s)
Vendor Selection
1
2
3
4
5
6
7
8
9
10
Implementation Planning and Design
1
2
3
4
5
6
7
8
9
10
System Build and Configuration
1
2
3
4
5
6
7
8
9
10
Training and Go Live
1
2
3
4
Stabilization and Optimization
1
2
3
4
Grant Completion
1
2
3
4
Cybersecurity and Privacy Plan
1
2
3
4
5
6
7
DxF Connectivity Plan
1
2
3
4
5
Reporting Plan
1
2
3
4
5
6

## C. Sample EHR Workplan
CalRHT EHR Modernization Grant — Workplan SAMPLE
Workplan Element | Activity | Person Responsible | Key Partners (if applicable) | Start Date | End Date | Interval (if applicable) | Outcome(s)
Vendor Selection |  |  |  | Est. Oct 2026 - Jan 2027
1 | Complete Technology Readiness Assessment
2 | Define Business Requirements
3 | Define Technical Requirements
4 | Issue EHR vendor RFP or Establish procurement process / Engage targeted vendors with detailed needs
5 | Define evaluation process and scoring
6 | Evaluate and Score Responses
7 | Conduct Vendor Demonstrations
8 | Select Vendor of choice
9 | Negotiate Contract and Milestones
10 | Execute Contract and Vendor Letter of Attestation (if needed)
Implementation Planning and Design |  |  |  | Est: Nov 2026 - Feb 2027
1 | ID & Assign project team
2 | Develop detailed project plan with timeline (based on vendor discussions), including go live check list
3 | Conduct workflow analysis (incl vendor)
4 | Design EHR configuration, template design and clinical documentation structure
5 | Plan interfaces and interoperability components w/timing (QHIOs, labs, pharmacy, etc)
6 | Develop data migration strategy (as applicable)
7 | Develop test plans (unit/functional, integration, end-to-end testing, reporting, clinical safety, Security/Privacy & any automation testing)
8 | Develop training plan (Admins/Super-Users, Staff, Leadership, others)
9 | Develop go live execution plan and support approach
10 | Develop change management and staff communication plan
System Build and Configuration |  |  |  | Est: Feb - Jun 2027
1 | Configure EHR per workflow design incl. templates, etc.
2 | Build interfaces (QHIOs, Labs, Pharmacy, etc)
3 | Execute data migration
4 | Test data Migration integrity
5 | Complete unit/functional testing
6 | Complete integration testing
7 | Conduct Clinical Safety and Security-Privacy testing
8 | Complete reporting testing
9 | Conduct use acceptance testing with clinical and admin staff
10 | Conduct Super-User training
Training and Go Live |  |  |  | Est: Jun-Aug 2027
1 | Deliver training to all staff in agreed to segments
2 | Review risks, issues, go live checklist and confirm go-live date
3 | Execute Go Live
4 | Provide onsite/at hand support as needed
Stabilization and Optimization |  |  |  | Est: Aug - Sept 2027
1 | Log, monitor and resolve critical issues
2 | Monitor and review integrations
3 | Review go live progress against productivity trajectory (reduced patient panels during go live)
4 | Continue to address issues via support
Grant Completion |  |  |  | 2027-09-01
1 | Confirm RHT program requirements met
2 | Submit all remaining reporting
3 | Confirm activation of sustainability plan
4 | Ensure grant payment processed by 9/30/2027
Cybersecurity and Privacy Plan |  |  |  | Est. Oct 2026 – Sep 2027 (ongoing)
1 | HIPAA Security Risk Assessment
2 | HICP self-assessment
3 | BAA + vendor vetting
4 | Cybersecurity and Privacy Plans including policies and remediation plan, acceptable use, data classification, incident reporting, patient rights (notice of privacy practices), remote access policies, etc.
5 | Workforce and Access controls at go-live (RBAC, MFA, audit logging, encryption, etc.)
6 | Technical controls at go-live
7 | Security Awareness Training
8 | Incident Response Plan and ongoing monitoring plan
9 | Business Continuity and Disaster Recovery Plan
DxF Connectivity Plan |  |  |  | Est. Oct 2026 – Sep 2027 (ongoing)
1 | Confirm current DSA (Data Sharing Agreement) signatory status
2 | Document current QHIO connection or national network participation status and identify applicable QHIO(s) or national networks
3 | Develop DxF data exchange and interoperability roadmap
4 | Submit QHIO or national network interface and connectivity specifications to EHR vendor during System Build
5 | Confirm DxF signature and data exchange readiness prior to Milestone 3 (Final Report)
Reporting Plan |  |  |  | Est. Oct 2026 – Sep 2027 (ongoing)
1 | Set up streamlined monthly subrecipient activity and financial reporting cadence
2 | Set up streamlined quarterly financial and performance reports
3 | Prepare Annual Activity Report
4 | Prepare Annual Financial Report
5 | Submit Interim Report with Milestone 2
6 | Submit Final Report with Milestone 3