## Sheet1
Below are some examples of how to complete the Building Milestones table based on the Compliance Type selected for each building: Compliance Type See Example SPC and NPC Retrofit (multiple buildings) ................................... 1A SPC and NPC Retrofit .................................................................... 1B NPC Retrofit .................................................................................... 2A NPC Retrofit (multiple buildings, one of which is NPC 5 only) .... 2B SPC Retrofit ..................................................................................... 3 2030 Compliant Building ............................................................... 4 Demolish Building .......................................................................... 5 No GAC services, convert to OSHPD 1R ....................................... 6 Relocate services to NEW building(s) .......................................... 7 Relocate services to other existing compliant building(s) ........ 8
Revision date 08/25/2025
Example 1A: Building Compliance Type: SPC and NPC Retrofit (multiple buildings) This facility has 2 buildings, BLD-00001 needs SPC 4D, NPC 4 and NPC 5 upgrade, and BLD-00002 needs NPC 4 and NPC 5 upgrade. Note on NPC 5 upgrade: Since NPC 5 upgrade applies to the entire facility (all buildings), it is not necessary to add an NPC 5 milestone for each building. Adding the NPC 5 milestone to at least one building is acceptable and will count toward the entire campus (in this example, it has been added to BLD-00002).
Example 1A - Building Milestones
| Milestone | Building No. | Milestone Type (drop-down selection) | Description (text field)
| 1 | BLD-00001 | Material Testing Report Submittal | MTCAP submittal
| 2 | BLD-00001 | Evaluation Report Submittal | SPC 4D SCU evaluation
| 3 | BLD-00001 | SPC/Demo/RACs Construction Project Submittal | SPC 4D upgrade construction document - regional project submittal
| 4 | BLD-00001 | Construction Milestone | SPC 4D upgrade construction project 20% completion milestone
| 5 | BLD-00001 | Construction Milestone | SPC 4D upgrade construction project 50% completion milestone
| 6 | BLD-00001 | Construction Final | SPC 4D upgrade construction project - construction final
| 7 | BLD-00001 | NPC 4/4D Construction Document Submittal | NPC 4/4D upgrade regional projects submittal
| 8 | BLD-00001 | NPC 4/4D Permit Issuance | Obtain NPC 4/4D upgrade permit(s)
| 9 | BLD-00001 | Construction Milestone | NPC 4/4D Construction 20% completion
| 10 | BLD-00001 | Construction Final | NPC 4/4D upgrade construction project final(s)
| Milestone | Building No. | Milestone Type (drop-down selection) | Description (text field)
| 1 | BLD-00002 | Evaluation Report Submittal | NPC 4/4D Evaluation Report submittal
| 2 | BLD-00002 | Evaluation Report Submittal | NPC 5 Evaluation Report submittal
| 3 | BLD-00002 | NPC 4/4D Construction Document Submittal | NPC 4 / 4D upgrade regional major projects submittal
| 4 | BLD-00002 | NPC 5 Construction Document Submittal | NPC 5 upgrade regional major projects submittal
| 5 | BLD-00002 | NPC 4/4D Permit Issuance | Obtain NPC 4/4D upgrade major project permit(s)
| 6 | BLD-00002 | NPC 5 Permit Issuance | Obtain NPC 5 upgrade major project permit(s)
| 7 | BLD-00002 | Construction Milestone | NPC 4/4D Construction 20% major project completion
| 8 | BLD-00002 | Construction Milestone | NPC 5 Construction 20% major project completion
| 9 | BLD-00002 | Construction Final | NPC 4/4D project(s) - completion of all related projects
| 10 | BLD-00002 | Construction Final | NPC 5 project(s) - completion of all related projects
Example 1B: Building Compliance Type: SPC and NPC Retrofit (singe building) This facility has 1 building, BLD-00001, which needs SPC 4D, NPC 4 and NPC 5 upgrade.
Example 1B - Building Milestones
| Milestone | Building No. | Milestone Type (drop-down selection) | Description (text field)
| 1 | BLD-00001 | Evaluation Report Submittal | SPC 4D SCU evaluation
| 2 | BLD-00001 | SPC/Demo/RACs Construction Project Submittal | SPC 4D upgrade construction document regional project submittal
| 3 | BLD-00001 | Construction Milestone | SPC 4D upgrade construction project 20% completion milestone
| 4 | BLD-00001 | Construction Final | SPC 4D upgrade construction project - construction final
| 5 | BLD-00001 | NPC 4/4D Construction Document Submittal | NPC 4 / 4D upgrade regional major projects submittal
| 6 | BLD-00001 | NPC 5 Construction Document Submittal | NPC 5 upgrade regional major projects submittal
| 7 | BLD-00001 | NPC 4/4D Permit Issuance | Obtain NPC 4/4D upgrade major project permit(s)
| 8 | BLD-00001 | Construction Milestone | NPC 4/4D Construction 20% major project completion
| 9 | BLD-00001 | Construction Milestone | NPC 5 Construction 20% major project completion
| 10 | BLD-00001 | Construction Final | NPC 4/4D project(s) and NPC 5 - completion of all related projects
Example 2A: Building Compliance Type: NPC Retrofit Building BLD-00010 requires both NPC 4 and NPC 5 upgrades.
Example 2A - Building Milestones
| Milestone | Building No. | Milestone Type (drop-down selection) | Description (text field)
| 1 | BLD-00010 | Evaluation Report Submittal | NPC 4/4D Evaluation Report submittal
| 2 | BLD-00010 | Evaluation Report Submittal | NPC 5 Evaluation Report submittal
| 3 | BLD-00010 | NPC 4/4D Construction Document Submittal | NPC 4 / 4D upgrade regional major projects submittal
| 4 | BLD-00010 | NPC 5 Construction Document Submittal | NPC 5 upgrade regional major projects submittal
| 5 | BLD-00010 | NPC 4/4D Permit Issuance | Obtain NPC 4/4D upgrade major project permit(s)
| 6 | BLD-00010 | NPC 5 Permit Issuance | Obtain NPC 5 upgrade major project permit(s)
| 7 | BLD-00010 | Construction Milestone | NPC 4/4D Construction 20% major project completion
| 8 | BLD-00010 | Construction Milestone | NPC 5 Construction 20% major project completion
| 9 | BLD-00010 | Construction Final | NPC 4/4D project(s) - completion of all related projects
| 10 | BLD-00010 | Construction Final | NPC 5 project(s) - completion of all related projects
Example 2B: Building Compliance Type: NPC Upgrade (Multiple buildings, one of which is NPC 5 upgrade only) This facility has two buildings, BLD-00375 needs NPC 4 and NPC 5 upgrade, and BLD-00400 needs NPC 5 upgrade only. In this example, the NPC 5 milestones have already been added to building BLD-00375. Since NPC 5 upgrade applies to the entire facility (all buildings), it is not necessary to add duplicate NPC 5 milestones to BLD-00400. Instead, it is permissible to enter only the Construction Final, with a note in the Description that references the building where the full NPC 5 milestones are listed. For example, "NPC 5 Project(s) - See building BLD-00375 for intermediate milestones".
Example 2B - Building Milestones
| Milestone | Building No. | Milestone Type (drop-down selection) | Description (text field)
| 1 | BLD-00375 | Evaluation Report Submittal | NPC 4/4D Evaluation Report submittal
| 2 | BLD-00375 | Evaluation Report Submittal | NPC 5 Evaluation Report submittal
| 3 | BLD-00375 | NPC 4/4D Construction Document Submittal | NPC 4 / 4D upgrade regional major projects submittal
| 4 | BLD-00375 | NPC 5 Construction Document Submittal | NPC 5 upgrade regional major projects submittal
| 5 | BLD-00375 | NPC 4/4D Permit Issuance | Obtain NPC 4/4D upgrade major project permit(s)
| 6 | BLD-00375 | NPC 5 Permit Issuance | Obtain NPC 5 upgrade major project permit(s)
| 7 | BLD-00375 | Construction Milestone | NPC 4/4D Construction 20% major project completion
| 8 | BLD-00375 | Construction Milestone | NPC 5 Construction 20% major project completion
| 9 | BLD-00375 | Construction Final | NPC 4/4D project(s) - completion of all related projects
| 10 | BLD-00375 | Construction Final | NPC 5 project(s) - completion of all related projects
| Milestone | Building No. | Milestone Type (drop-down selection) | Description (text field)
| 1 | BLD-00400 | Construction Final | NPC 5 project(s) - See BLD-00002 for intermediate milestones.
| 2 | BLD-00400 | N/A
| 3 | BLD-00400 | N/A
| 4 | BLD-00400 | N/A
| 5 | BLD-00400 | N/A
| 6 | BLD-00400 | N/A
| 7 | BLD-00400 | N/A
| 8 | BLD-00400 | N/A
| 9 | BLD-00400 | N/A
| 10 | BLD-00400 | N/A
Example 3: Building Compliance Type: SPC Retrofit Building BLD-00025 is currently SPC 2 and NPC 5, so it only needs SPC 4D upgrade.
Example 3 - Building Milestones
| Milestone | Building No. | Milestone Type (drop-down selection) | Description (text field)
| 1 | BLD-00025 | Material Testing Report Submittal | MTCAP submittal
| 2 | BLD-00025 | Evaluation Report Submittal | SPC 4D evaluation submittal
| 3 | BLD-00025 | Material Testing Report Submittal | MTCAR submittal
| 4 | BLD-00025 | SPC/Demo/RACs Construction Project Submittal | SPC 4D upgrade construction document - regional project submittal
| 5 | BLD-00025 | SPC/Demo/RACs Permit Issuance | Obtain SPC 4D project building permit
| 6 | BLD-00025 | Construction Milestone | SPC 4D Construction 20% completion
| 7 | BLD-00025 | Construction Milestone | SPC 4D Construction 50% completion
| 8 | BLD-00025 | Construction Final | SPC 4D Construction Final
| 9 | BLD-00025 | N/A
| 10 | BLD-00025 | N/A
Example 4: Building Compliance Type: 2030 Compliant Building BLD-00100 has met the 2030 requirements. For this building, only the first milestone is required indicating that the building is 2030 compliant.
Example 4 - Building Milestones
| Milestone | Building No. | Milestone Type (drop-down selection) | Description (text field)
| 1 | BLD-00100 | 2030 Compliant Building | Already compliant
| 2 | BLD-00100 | N/A
| 3 | BLD-00100 | N/A
| 4 | BLD-00100 | N/A
| 5 | BLD-00100 | N/A
| 6 | BLD-00100 | N/A
| 7 | BLD-00100 | N/A
| 8 | BLD-00100 | N/A
| 9 | BLD-00100 | N/A
| 10 | BLD-00100 | N/A
Example 5: Building Compliance Type: Demolish Building Building BLD-00200 will be demolished.
Example 5 - Building Milestones
| Milestone | Building No. | Milestone Type (drop-down selection) | Description (text field)
| 1 | BLD-00200 | Evaluation Report Submittal | Submitting Intent to remove GAC Services letter from facility in a SCU project
| 2 | BLD-00200 | SPC/Demo/RACs Construction Project Submittal | Demolition regional project submittal
| 3 | BLD-00200 | SPC/Demo/RACs Permit Issuance | Obtain demolition regional project permit
| 4 | BLD-00200 | Construction Milestone | Demolition Construction - Utilities are severed to a point that the building is not usable.
| 5 | BLD-00200 | Construction Milestone | Demolition Construction 20% completion
| 6 | BLD-00200 | Construction Milestone | Demolition Construction 50% completion
| 7 | BLD-00200 | Construction Final | Demolition construction final
| 8 | BLD-00200 | N/A
| 9 | BLD-00200 | N/A
| 10 | BLD-00200 | N/A
Example 6: Building Compliance Type: Rerouting utilities, no GAC Services, convert to OSHPD 1R or transfer to the local jurisdiction having authority BLD-00350 has no GAC services in the building, but utilities and/or egress require construction.
OR
Example 7: Building Compliance Type: Relocate services to NEW Building(s) BLD-00350 has GAC services in the building, and utilities and/or egress require construction. The ultimate goal is to convert to OSHPD 1R or transfer it to the local jurisdiction having authority.
OR
Example 8: Building Compliance Type: Relocate services to other existing compliant building(s) BLD-00350 has GAC services in the building, and utilities and/or egress require construction. The ultimate goal is to convert to OSHPD 1R or transfer it to the local jurisdiction having authority.
Example 6, 7, 8 - Building Milestones
| Milestone | Building No. | Milestone Type (drop-down selection) | Description (text field)
| 1 | BLD-00350 | Evaluation Report Submittal | Submitting Intent to remove GAC Services letter from facility in a SCU project
| 2 | BLD-00350 | SPC/Demo/RACs Construction Project Submittal | Regional project submittal
| 3 | BLD-00350 | SPC/Demo/RACs Permit Issuance | Obtain building permit
| 4 | BLD-00350 | Construction Milestone | Construction 20% completion
| 5 | BLD-00350 | Construction Milestone | Construction 50% completion
| 6 | BLD-00350 | Construction Final | Construction final
| 7 | BLD-00350 | N/A
| 8 | BLD-00350 | N/A
| 9 | BLD-00350 | N/A
| 10 | BLD-00350 | N/A