## Sheet1
Compliance Type Case 1A: SPC and NPC Retrofit (USE THIS IF THERE IS MORE THAN ONE GAC BUILDING IN THE CAMPUS) | This facility has two buildings with one needing SPC 4D, NPC 4 and NPC 5 upgrade. And the other needing NPC 4 and NPC 5 upgrade only. It is acceptable to put only one NPC 5 milestones in one building since it applies to the whole facility. | Drop list values | Free-field text
| Building No. | Milestone Type | Description
1 | BLD-0xxxx | Evaluation Report Submittal | MTCAP submittal
2 | BLD-0xxxx | Evaluation Report Submittal | SPC 4D SCU evaluation
3 | BLD-0xxxx | Construction Project Submittal | SPC 4D upgrade construction project submittal
4 | BLD-0xxxx | Construction Milestone | SPC 4D upgrade construction project 20% completion milestone
5 | BLD-0xxxx | Construction Milestone | SPC 4D upgrade construction project 50% completion milestone
6 | BLD-0xxxx | Construction Final | SPC 4D upgrade construction project - construction final
7 | BLD-0xxxx | Construction Project Submittal | NPC 4/4D upgrade regional projects submittal
8 | BLD-0xxxx | Permit Issuance | Obtain NPC 4/4D upgrade permit(s)
9 | BLD-0xxxx | Construction Milestone | NPC 4/4D Construction 20% completion
10 | BLD-0xxxx | Construction Final | NPC 4/4D upgrade construction project final(s)
Building No.
1 | BLD-0yyyy | Evaluation Report Submittal | NPC 4/4D Evaluation Report submittal
2 | BLD-0yyyy | Evaluation Report Submittal | NPC 5 Evaluation Report submittal
3 | BLD-0yyyy | NPC 4/4D Construction Document Submittal | NPC 4 / 4D upgrade regional major projects submittal
4 | BLD-0yyyy | NPC 5 Construction Document Submittal | NPC 5 upgrade regional major projects submittal
5 | BLD-0yyyy | NPC 4/4D Permit Issuance | Obtain NPC 4/4D upgrade major project permit(s)
6 | BLD-0yyyy | NPC 5 Permit Issuance | Obtain NPC 5 upgrade major project permit(s)
7 | BLD-0yyyy | Construction Milestone | NPC 4/4D Construction 20% major project completion
8 | BLD-0yyyy | Construction Milestone | NPC 5 Construction 20% major project completion
9 | BLD-0yyyy | Construction Final | NPC 4/4D project(s) - completion of all related projects
10 | BLD-0yyyy | Construction Final | NPC 5 project(s) - completion of all related projects
Compliance Type Case 1B: SPC and NPC Retrofit (USE THIS IF THERE IS ONLY ONE GAC BUILDING IN THE CAMPUS) | This facility has two buildings with one needing SPC 4D, NPC 4 and NPC 5 upgrade. And the other needing NPC 4 and NPC 5 upgrade. It is acceptable to put only one NPC 5 milestones in one building since it applies to the whole facility.
| Building No. | Milestone Type | Description
1 | BLD-0xxxx | Evaluation Report Submittal | SPC 4D SCU evaluation
2 | BLD-0xxxx | Construction Project Submittal | SPC 4D upgrade construction project submittal
3 | BLD-0xxxx | Construction Milestone | SPC 4D upgrade construction project 20% completion milestone
4 | BLD-0xxxx | Construction Final | SPC 4D upgrade construction project - construction final
5 | BLD-0xxxx | NPC 4/4D Construction Document Submittal | NPC 4 / 4D upgrade regional major projects submittal
6 | BLD-0xxxx | NPC 5 Construction Document Submittal | NPC 5 upgrade regional major projects submittal
7 | BLD-0xxxx | NPC 4/4D Permit Issuance | Obtain NPC 4/4D upgrade major project permit(s)
8 | BLD-0xxxx | Construction Milestone | NPC 4/4D Construction 20% major project completion
9 | BLD-0xxxx | Construction Milestone | NPC 5 Construction 20% major project completion
10 | BLD-0xxxx | Construction Final | NPC 4/4D project(s) and NPC 5 - completion of all related projects
Compliance Type Case 2: NPC Retrofit | NPC retrofit (both NPC 4 and NPC 5 upgrades) NPC 5 upgrade only similar | Milestone Type | Description
| Building No. | Evaluation Report Submittal | NPC 4/4D Evaluation Report submittal
1 | BLD-0xxxx | Evaluation Report Submittal | NPC 5 Evaluation Report submittal
2 | BLD-0xxxx | NPC 4/4D Construction Document Submittal | NPC 4 / 4D upgrade regional major projects submittal
3 | BLD-0xxxx | NPC 5 Construction Document Submittal | NPC 5 upgrade regional major projects submittal
4 | BLD-0xxxx | NPC 4/4D Permit Issuance | Obtain NPC 4/4D upgrade major project permit(s)
5 | BLD-0xxxx | NPC 5 Permit Issuance | Obtain NPC 5 upgrade major project permit(s)
6 | BLD-0xxxx | Construction Milestone | NPC 4/4D Construction 20% major project completion
7 | BLD-0xxxx | Construction Milestone | NPC 5 Construction 20% major project completion
8 | BLD-0xxxx | Construction Final | NPC 4/4D project(s) - completion of all related projects
9 | BLD-0xxxx | Construction Final | NPC 5 project(s) - completion of all related projects
10 | BLD-0xxxx
Compliance Type Case 3: SPC 4D Retrofit | This is the case where the building is SPC 2 and NPC 5.
| Building No. | Milestone Type | Description
1 | BLD-0xxxx | Evaluation Report Submittal | MTCAP submittal
2 | BLD-0xxxx | Evaluation Report Submittal | SPC 4D evaluation submittal
3 | BLD-0xxxx | Evaluation Report Submittal | MTCAR submittal
4 | BLD-0xxxx | Construction Project Submittal | SPC 4D upgrade regional project submittal
5 | BLD-0xxxx | Permit Issuance | Obtain SPC 4D project building permit
6 | BLD-0xxxx | Construction Milestone | SPC 4D Construction 20% completion
7 | BLD-0xxxx | Construction Milestone | SPC 4D Construction 50% completion
8 | BLD-0xxxx | Construction Final | SPC 4D Construction Final
9 | BLD-0xxxx
10 | BLD-0xxxx
Compliance Type Case 4: 2030 Compliant | This case is where some buildings have met 2030 requirements. For those buildings there is no need to fill the building milestones other than the first line.
| Building No. | Milestone Type | Description
1 | BLD-0xxxx | 2030 Compliant Building | Already compliant
2 | BLD-0xxxx | N/A
3 | BLD-0xxxx | N/A
4 | BLD-0xxxx | N/A
5 | BLD-0xxxx | N/A
6 | BLD-0xxxx | N/A
7 | BLD-0xxxx | N/A
8 | BLD-0xxxx | N/A
9 | BLD-0xxxx | N/A
10 | BLD-0xxxx
Compliance Type Case 5: Demolish Building
| Building No. | Milestone Type | Description
1 | BLD-0xxxx | Evaluation Report Submittal | Submitting Intent to remove GAC Services letter from facility in a SCU project.
2 | BLD-0xxxx | Construction Project Submittal | Demolition regional project submittal
3 | BLD-0xxxx | Permit Issuance | Obtain demolition regional project permit
4 | BLD-0xxxx | Construction Milestone | Demolition Construction - Utiliies are severed to a point that the building is not usable.
5 | BLD-0xxxx | Construction Milestone | Demolition Construction 20% completion
6 | BLD-0xxxx | Construction Milestone | Demolition Construction 50% completion
7 | BLD-0xxxx | Construction Final | Demolition construction final
8 | BLD-0xxxx | N/A
9 | BLD-0xxxx | N/A
10 | BLD-0xxxx
Compliance Type Case 6: No GAC Services, convert to OSHPD 1R | This case is where there is no GAC services in the building, but utilities and/or egress require construction.
Compliance Type Case 7: Relocate Services to New Building(s) | This case is where there are GAC services in the building, and utilities and/or egress require construction. The ultimate goal is to convert to OSHPD 1R or transfer it to the local jurisdiction having authority.
Compliance Type Case 8: Relocate Services to Other Existing Compliant Building(s) | This case is where there are GAC services in the building, and utilities and/or egress require construction. The ultimate goal is to convert to OSHPD 1R or transfer it to the local jurisdiction having authority.
| Building No. | Milestone Type | Description
1 | BLD-0xxxx | Evaluation Report Submittal | Submitting Intent to remove GAC Services letter from facility in a SCU project
2 | BLD-0xxxx | Construction Project Submittal | Regional project submittal
3 | BLD-0xxxx | Construction Permit | Obtain building permit
4 | BLD-0xxxx | Construction Milestone | Construction 20% completion
5 | BLD-0xxxx | Construction Milestone | Construction 50% completion
6 | BLD-0xxxx | Construction Final | Construction final
7 | BLD-0xxxx | N/A
8 | BLD-0xxxx | N/A
9 | BLD-0xxxx | N/A
10 | BLD-0xxxx

## Sheet2
1
1
1
1
1
1
1
2
2
2
2
2
2
2
3
3
3
3
3
3
3
4
4
4
4
4
4
4
5
5
5
5
5
5
5
6
6
6
6
6
6
6
7
7
7
7
7
7
7
8
8
8
8
8
8
8
9
9
9
9
9
9
9
10
10
10
10
10
10
10
Compliance Type Case 1: SPC and NPC Retrofit
Compliance Type Case 2: NPC Retrofit
Compliance Type Case 3: SPC Retrofit
Compliance Type Case 4: Compliant
Compliance Type Case 5: Demolish Building
Compliance Type Case 6: No GAC Services, convert to OSHPD 1R
Compliance Type Case 7: Relocate Services to New Building(s)
Compliance Type Case 8: Relocate Services to Other Existing Compliant Building(s)